## Start Here
Riverside Medical Center: Information Security Risk Assessment
Risk register, control gap assessment, and vendor tiering. Riverside is a fictional organization created for a portfolio project.
Assessment period: September 2026 ¦ Methodology: NIST SP 800-30 Rev. 1 ¦ Control frameworks: HIPAA Security Rule (45 CFR Part 164 Subpart C), NIST CSF 2.0, HHS 405(d) HICP
How to use this workbook
1. Asset Register: assets and Criticality/Vulnerability scores carried over from the 'Beyond Our Walls' TPRM presentation (ESRM Steps 1-2).
2. Risk Register: each risk scored for Likelihood (1-5) and Impact (1-5). Score and rating calculate automatically. Blank rows at the bottom are ready for new risks.
3. Heat Map: counts of risks in each Likelihood x Impact cell, before (inherent) and after (residual) treatment. Updates automatically.
4. Control Gap Assessment: key safeguards mapped to HIPAA, NIST CSF 2.0, and HICP, with current implementation status.
5. Vendor Tiering: sample vendors scored on four criteria; tier and monitoring requirement calculate automatically.
Legend
Blue text | Input you can edit (scores, statuses, text)
Black text | Formula: calculates automatically, do not overwrite
Yellow fill | Threshold settings that drive the formulas
Likelihood scale (probability the risk occurs within 12 months)
Score | Level | Definition
1 | Rare | Not expected; no known precedent in the sector
2 | Unlikely | Could occur; limited sector precedent
3 | Possible | Has occurred at comparable hospitals; controls partially effective
4 | Likely | Occurs regularly across the sector; controls weak or unverified
5 | Almost Certain | Actively exploited in healthcare now; no effective control in place
Impact scale (worst credible effect on Riverside)
Score | Level | Definition
1 | Negligible | No PHI exposure; no care disruption; cost under $10K
2 | Minor | Limited PHI (<500 records); brief disruption of a non-clinical function
3 | Moderate | Reportable breach (500+ records) or one-day disruption of a clinical or revenue function
4 | Major | Multi-day disruption to clinical care or revenue cycle; regulatory investigation likely
5 | Severe | Patient harm possible; weeks-long outage or large-scale breach; major penalties and lasting reputational damage
Risk rating thresholds (Score = Likelihood x Impact)
Minimum score | Rating | Required response
20 | Critical | Treat immediately; executive owner; report to board
12 | High | Treatment plan within 30 days; tracked by governance subcommittee
6 | Medium | Treat within 12 months or formally accept
1 | Low | Monitor; may be accepted by risk owner
Vendor tier thresholds (Total of four criteria, max 12)
Minimum total | Tier | Monitoring requirement
10 | Critical | Continuous monitoring + annual on-site/virtual audit + SOC 2 Type II or HITRUST
7 | High | Continuous monitoring + annual evidence review
4 | Medium | Continuous monitoring from Phase 3 + annual questionnaire
0 | Low | Questionnaire at onboarding and renewal

## Asset Register
Asset Register (ESRM Steps 1-2)
Source: Criticality and Vulnerability scores (1-10) from the author's 'Beyond Our Walls' TPRM presentation, slide 5.
Asset ID | Asset | Description | Asset Owner | Criticality (1-10) | Vulnerability (1-10) | Priority Score | Priority Rank
A1 | Claims, Billing & Clinical Data Systems | EHR, revenue-cycle, and claims/e-prescribing systems reachable through 1,300+ vendor relationships | CIO | 9 | 9 | 81 | 1
A2 | Controlled-Substance Inventory | Opioids and benzodiazepines managed via 12 Automated Dispensing Cabinets | Director of Pharmacy | 9 | 6 | 54 | 2
A3 | Blood Bank & Biologics | On-site blood product storage supporting surgery and trauma care | Laboratory Director | 7 | 4 | 28 | 6
A4 | Radioactive Materials | Nuclear-medicine and oncology sealed sources and isotopes | Radiation Safety Officer | 8 | 3 | 24 | 7
A5 | Physical Campus & Infrastructure | Power, medical gas, HVAC, and network backbone supporting the main campus | VP Facilities | 8 | 4 | 32 | 4
A6 | Workforce & Key Personnel | Clinical staff and physicians whose availability and safety are mission-critical | Chief Human Resources Officer | 7 | 3 | 21 | 8
A7 | Brand Reputation & Patient Trust | Community standing and patient confidence in Riverside's care | Chief Communications Officer | 6 | 5 | 30 | 5
A8 | Medical Device & IoT Fleet | Imaging, infusion pumps, and monitors remotely serviced and patched by device vendors | Director of Biomedical Engineering | 7 | 6 | 42 | 3

## Risk Register
Risk Register
Inherent = risk with current controls only. Residual = expected risk after the recommended controls are fully implemented. Target dates align with the TPRM program phases (Phase 1: Nov 2026, Phase 2: May 2027, Phase 3: Jan 2028).
Risk ID | Asset | Risk Title | Threat Source | Vulnerability | Existing Controls | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Rating | Treatment | Recommended Controls | HIPAA Reference | NIST CSF 2.0 | Risk Owner | Target Date | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Status
R01 | A1 | Ransomware via compromised vendor remote access | Ransomware affiliate (external, financially motivated) | Vendor remote-access accounts not required to use MFA; access never verified at onboarding | Annual BAA renewal; vendor self-attestation questionnaire | 5 | 5 | 25 | Critical | Mitigate | Require phishing-resistant MFA for all vendor remote access; brokered/just-in-time vendor access; continuous monitoring of Critical-tier vendors | 164.308(b)(1); 164.312(d) | GV.SC; PR.AA | CISO | May 2027 | 2 | 5 | 10 | Medium | In Progress
R02 | A1 | Prolonged outage of claims clearinghouse halts revenue and e-prescribing | Third-party service failure (ransomware or outage at vendor) | Single clearinghouse with no tested failover; no manual downtime procedures for claims or e-prescribing | Vendor SLA (no security or recovery terms) | 4 | 5 | 20 | Critical | Mitigate | Pre-contract a secondary clearinghouse; document and drill manual downtime procedures; maintain cash-reserve plan | 164.308(a)(7)(ii)(B)-(C) | GV.SC; RC.RP | CFO | Nov 2026 | 3 | 3 | 9 | Medium | In Progress
R03 | A1 | Business Associate Agreements lack enforceable security terms | Regulatory / contractual | BAAs contain no minimum controls, audit rights, or breach-notification SLA | Standard HIPAA BAA template | 4 | 4 | 16 | High | Mitigate | Modernized BAA: MFA certification, SOC 2 Type II or HITRUST evidence, 24-hour incident notification, audit rights | 164.308(b)(1); 164.314(a) | GV.SC | General Counsel | Nov 2026 | 2 | 4 | 8 | Medium | In Progress
R04 | A1 | Compromise of a vendor's subcontractor (fourth party) | External attacker targeting the vendor's supply chain | No visibility into subcontractors used by Critical-tier vendors | None | 3 | 4 | 12 | High | Mitigate | Require Critical-tier vendors to disclose material subcontractors and flow down equivalent security requirements | 164.314(a)(2)(i)(B) | GV.SC | Director of Procurement | May 2027 | 2 | 4 | 8 | Medium | Not Started
R05 | A1 | Workforce credentials stolen through phishing | Phishing campaign (external) | Inconsistent MFA on webmail and EHR remote access; annual-only awareness training | Email spam filter; annual HIPAA training | 4 | 4 | 16 | High | Mitigate | MFA on all remote and email access; monthly phishing simulations; external-sender banners; phishing report button | 164.308(a)(5); 164.312(d) | PR.AA; PR.AT | CISO | Nov 2026 | 2 | 4 | 8 | Medium | In Progress
R06 | A1 | Ransomware spreads through unpatched internal systems | Ransomware affiliate (external) | Patch cycle exceeds 60 days for critical vulnerabilities; flat network segments | Endpoint antivirus; monthly patch window | 3 | 5 | 15 | High | Mitigate | Risk-based patching SLA (critical in 14 days); EDR on all endpoints; network segmentation of clinical systems | 164.308(a)(1)(ii)(B); 164.308(a)(5)(ii)(B) | ID.RA; PR.PS; PR.IR | Director of IT Infrastructure | May 2027 | 2 | 5 | 10 | Medium | Not Started
R07 | A1 | EHR data cannot be restored after a destructive attack | Ransomware / destructive malware | Backups not immutable; restore never tested end-to-end | Nightly backups to on-premises storage | 3 | 5 | 15 | High | Mitigate | Immutable, offline-isolated backups; quarterly restore tests with documented recovery times | 164.308(a)(7)(ii)(A)-(B) | PR.DS; RC.RP | Director of IT Infrastructure | May 2027 | 2 | 4 | 8 | Medium | Not Started
R08 | A1 | Former workforce or vendor accounts remain active | Former employee, contractor, or attacker using stale credentials | No automated deprovisioning; vendor accounts not tied to contract end dates | Manual termination checklist | 4 | 4 | 16 | High | Mitigate | Automate HR-driven deprovisioning; quarterly access reviews; vendor accounts expire with contract | 164.308(a)(3)(ii)(C); 164.308(a)(4) | PR.AA | Director of Identity & Access | Nov 2026 | 2 | 3 | 6 | Medium | In Progress
R09 | A1 | Inappropriate employee access to patient records | Insider (curiosity, personal relationship, or malicious) | Audit logs collected but not proactively reviewed | Role-based EHR access; confidentiality agreement | 4 | 3 | 12 | High | Mitigate | Automated EHR access monitoring (e.g., VIP and coworker record alerts); sanctions policy enforcement | 164.312(b); 164.308(a)(1)(ii)(D) | DE.CM; PR.AA | Privacy Officer | May 2027 | 2 | 3 | 6 | Medium | Not Started
R10 | A8 | Medical devices compromised through vendor maintenance connections | External attacker or compromised device vendor | Device vendors keep always-on remote access; devices on shared network; legacy OS on some imaging systems | Device inventory (partial) | 3 | 5 | 15 | High | Mitigate | Complete device inventory; segment medical devices; vendor remote access only through brokered, logged sessions | 164.308(a)(1)(ii)(A); 164.312(a)(1) | ID.AM; PR.IR; GV.SC | Director of Biomedical Engineering | Jan 2028 | 2 | 4 | 8 | Medium | Not Started
R11 | A2 | Controlled-substance diversion from Automated Dispensing Cabinets | Insider (clinical staff) | Override reports reviewed inconsistently; shared credentials on some units | ADC badge + PIN access; monthly pharmacy reconciliation | 3 | 4 | 12 | High | Mitigate | Diversion analytics on ADC transactions; ban shared credentials; biometric ADC login | N/A (DEA / state pharmacy rules) | PR.AA; DE.CM | Director of Pharmacy | May 2027 | 2 | 3 | 6 | Medium | Not Started
R12 | A5 | Hurricane or extended power loss disrupts campus and on-site data center | Natural hazard (Gulf Coast hurricane season) | Single on-site data center; generator fuel supply for ~72 hours | Backup generators; emergency operations plan | 3 | 5 | 15 | High | Mitigate | Secondary hosting site or cloud failover for EHR; fuel resupply contracts; annual hurricane tabletop exercise | 164.308(a)(7)(ii)(B)-(C) | RC.RP; ID.IM | VP Facilities | Jan 2028 | 3 | 3 | 9 | Medium | Not Started
R13 | A1 | Third-party incident not covered by incident response plan | Any third-party security incident | IR plan written for internal incidents only; never exercised with vendors | Internal incident response plan | 3 | 4 | 12 | High | Mitigate | Add third-party incident playbook; joint tabletop with Critical-tier vendors annually | 164.308(a)(6) | RS.MA; RS.CO | CISO | May 2027 | 2 | 3 | 6 | Medium | Not Started
R14 | A1 | Lost or stolen laptop exposes PHI | Theft or loss (opportunistic) | Full-disk encryption not enforced on all laptops | Encryption on most new devices; asset tags | 3 | 3 | 9 | Medium | Mitigate | Enforce full-disk encryption via device management; remote wipe capability | 164.312(a)(2)(iv); 164.310(d)(1) | PR.DS | Director of IT Infrastructure | Nov 2026 | 1 | 2 | 2 | Low | In Progress
R15 | A4 | Theft or loss of radioactive sealed sources | Malicious actor or insider | Sources stored in controlled areas; inventory checks periodic | Locked storage; NRC-required inventories; badge access | 1 | 5 | 5 | Low | Accept | Maintain current NRC/state program controls; reassess annually | N/A (NRC 10 CFR Part 37) | PR.AA (physical) | Radiation Safety Officer | Annual review | 1 | 5 | 5 | Low | Accepted
R16
R17
R18
R19
R20

## Heat Map
Risk Heat Maps
Each cell counts how many risks fall at that Likelihood x Impact position. Updates automatically from the Risk Register.
Inherent risk (current state) | [5 empty] | Risk count by rating
Impact ↓ / Likelihood → | 1 | 2 | 3 | 4 | 5 | Rating | Inherent | Residual
5 | 1 | 0 | 4 | 1 | 1 | Critical | 2 | 0
4 | 0 | 0 | 3 | 3 | 0 | High | 11 | 0
3 | 0 | 0 | 1 | 1 | 0 | Medium | 1 | 13
2 | 0 | 0 | 0 | 0 | 0 | Low | 1 | 2
1 | 0 | 0 | 0 | 0 | 0 | Total | 15 | 15
Average risk score
Residual risk (after recommended controls) | [5 empty] | Inherent | 14.3333
Impact ↓ / Likelihood → | 1 | 2 | 3 | 4 | 5 | Residual | 7.2667
5 | 1 | 2 | 0 | 0 | 0 | Reduction | 49.3%
4 | 0 | 5 | 0 | 0 | 0
3 | 0 | 4 | 2 | 0 | 0
2 | 1 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0

## Control Gap Assessment
Control Gap Assessment
Status reflects the assessed state in September 2026. Evidence notes describe what was reviewed or what is missing.
Control ID | Control | HIPAA Reference | NIST CSF 2.0 | HHS 405(d) HICP Practice | Status | Evidence / Gap Notes | Related Risks | Priority | Summary
C01 | Multi-factor authentication for all remote, email, and vendor access | 164.312(d) | PR.AA | Access Management | Partial | MFA on VPN for employees only; vendor portals and webmail exempt | R01, R05 | High | Implemented | 1 | 7.143%
C02 | Vendor inventory and risk-based tiering | 164.308(b)(1); 164.308(a)(1)(ii)(A) | GV.SC | Cybersecurity Oversight and Governance | Not Implemented | Vendor list kept by Procurement for payment, not security; no tiers | R01, R03, R04 | High | Partial | 10 | 71.43%
C03 | Business Associate Agreements with minimum security requirements | 164.308(b)(1); 164.314(a) | GV.SC | Cybersecurity Oversight and Governance | Partial | BAAs signed for PHI vendors but use 2013 template without security terms | R03 | High | Not Implemented | 3 | 21.43%
C04 | Continuous monitoring of Critical- and High-tier vendors | 164.308(a)(1)(ii)(D) | DE.CM; GV.SC | Cybersecurity Oversight and Governance | Not Implemented | Annual self-attestation questionnaire only | R01, R04 | High | Total | 14
C05 | Security awareness training and phishing simulation | 164.308(a)(5) | PR.AT | Email Protection | Partial | Annual HIPAA module completed by 91% of staff; no phishing simulations | R05 | Medium
C06 | Risk-based vulnerability and patch management | 164.308(a)(1)(ii)(B) | ID.RA; PR.PS | Vulnerability Management | Partial | Monthly patching; median 63 days to remediate critical findings | R06 | High
C07 | Immutable backups with tested restoration | 164.308(a)(7)(ii)(A) | PR.DS; RC.RP | Data Protection and Loss Prevention | Partial | Nightly backups exist; no immutable copy; last full restore test: never | R07 | High
C08 | Contingency and downtime procedures (incl. third-party outages) | 164.308(a)(7)(ii)(B)-(C) | RC.RP | Security Operations Center and Incident Response | Not Implemented | No manual procedures for claims or e-prescribing downtime | R02, R12 | High
C09 | Access provisioning, deprovisioning, and periodic review | 164.308(a)(3)(ii)(C); 164.308(a)(4) | PR.AA | Access Management | Partial | Manual termination checklist; 47 active accounts found for departed staff in sample | R08 | High
C10 | Audit log review and EHR access monitoring | 164.312(b) | DE.CM | Security Operations Center and Incident Response | Partial | Logs retained 1 year; reviewed only after complaints | R09 | Medium
C11 | Medical device inventory and network segmentation | 164.308(a)(1)(ii)(A); 164.312(a)(1) | ID.AM; PR.IR | Network Connected Medical Devices | Partial | Inventory ~70% complete; devices share clinical VLANs | R10 | Medium
C12 | Incident response plan covering third-party incidents | 164.308(a)(6) | RS.MA; RS.CO | Security Operations Center and Incident Response | Partial | Internal IR plan exists; no vendor playbook; last tabletop 2023 | R13 | Medium
C13 | Endpoint encryption and device management | 164.312(a)(2)(iv) | PR.DS | Endpoint Protection | Partial | Encryption on ~85% of laptops; not enforced by policy | R14 | Medium
C14 | Enterprise risk analysis performed and documented annually | 164.308(a)(1)(ii)(A) | ID.RA; GV.RM | Cybersecurity Oversight and Governance | Implemented | This assessment; to be repeated annually by the Vendor Risk Governance Subcommittee | All | Low

## Vendor Tiering
Vendor Tiering (sample of Critical-path and representative vendors)
Score each criterion 0-3 (0 = none, 3 = extensive). 'Critical by default' = Yes forces Critical tier (clearinghouse and EHR vendors, per the TPRM program design). Vendor names are generic placeholders.
Vendor ID | Vendor (generic) | Service Provided | PHI Access (0-3) | System Integration (0-3) | Operational Criticality (0-3) | Remote Access (0-3) | Total (0-12) | Critical by Default? | Tier | Monitoring Requirement | BAA Required?
V01 | Claims Clearinghouse | Claims submission, prior authorization, e-prescribing routing | 3 | 3 | 3 | 3 | 12 | Yes | Critical | Continuous monitoring + annual on-site/virtual audit + SOC 2 Type II or HITRUST | Yes
V02 | EHR Platform Vendor | Electronic health record hosting and support | 3 | 3 | 3 | 3 | 12 | Yes | Critical | Continuous monitoring + annual on-site/virtual audit + SOC 2 Type II or HITRUST | Yes
V03 | Revenue Cycle Outsourcer | Coding, billing, and denial management | 3 | 2 | 3 | 2 | 10 | No | Critical | Continuous monitoring + annual on-site/virtual audit + SOC 2 Type II or HITRUST | Yes
V04 | Dispensing Cabinet Vendor | Automated Dispensing Cabinets and pharmacy software | 2 | 2 | 3 | 3 | 10 | No | Critical | Continuous monitoring + annual on-site/virtual audit + SOC 2 Type II or HITRUST | Yes
V05 | Imaging / PACS Vendor | Picture archiving system and remote support | 2 | 2 | 2 | 3 | 9 | No | High | Continuous monitoring + annual evidence review | Yes
V06 | Infusion Pump Manufacturer | Pump fleet, drug library updates, remote patching | 1 | 2 | 3 | 3 | 9 | No | High | Continuous monitoring + annual evidence review | Yes
V07 | Cloud Backup Provider | Offsite backup storage for clinical systems | 3 | 2 | 3 | 1 | 9 | No | High | Continuous monitoring + annual evidence review | Yes
V08 | Building Automation Contractor | HVAC and building management systems | 0 | 2 | 2 | 3 | 7 | No | High | Continuous monitoring + annual evidence review | No
V09 | Medical Transcription Service | Dictation transcription for physicians | 3 | 1 | 1 | 1 | 6 | No | Medium | Continuous monitoring from Phase 3 + annual questionnaire | Yes
V10 | Collections Agency | Patient account collections | 2 | 1 | 1 | 0 | 4 | No | Medium | Continuous monitoring from Phase 3 + annual questionnaire | Yes
V11 | Clinical Staffing Agency | Travel nurse and locum placement (placed staff are treated as workforce, not a Business Associate) | 0 | 0 | 2 | 0 | 2 | No | Low | Questionnaire at onboarding and renewal | No
V12 | Linen & Laundry Service | Linen supply and laundering | 0 | 0 | 1 | 0 | 1 | No | Low | Questionnaire at onboarding and renewal | No
V13 | Food Service Contractor | Cafeteria and patient meal service | 0 | 0 | 1 | 0 | 1 | No | Low | Questionnaire at onboarding and renewal | No
Tier summary
Critical | 4
High | 4
Medium | 2
Low | 3